## Sheet1
BILL OF QUANTITIES
Name of Contractor or supplier : | M/s Seema Electrical Udaipur
Name of Work ;- | Electric Repair and MTC work at Govt. Ambedkar hostel Ambamata, Govardhanvilas, Udaipur
Serial No. of this bill : | First & Final Bill
No. and date of the last bill- | Not Applicable
Reference to work order or Agreement : | 1179 Dt. 09-01-2025
Agreement No. | 48/2024-25
Date of written order to commence work : | 09-01-2025
St. date of Start : | 18-01-2025
St. date of completion : | 17-04-2025
Date of actual completion of work : | 01-03-2025
Date of measurement : | 03-03-2025
WORK ORDER AMOUNT RS. | 854678
ITEM DETAILS
S_No | Item_Description | Unit | Work_Order_Qty | Work_Order_Rate | Bill_Qty | Bill_Rate | Work_Order_Amount | Bill_Amount
1 | LED lights installation - 20W | Nos | 10 | 1200 | 12 | 1200 | 12000 | 14400
2 | Electrical wiring - 2.5 sq mm | Meter | 500 | 45 | 520 | 45 | 22500 | 23400
3 | Switch board installation | Nos | 15 | 850 | 15 | 850 | 12750 | 12750
4 | Earthing work | Job | 2 | 3500 | 2 | 3500 | 7000 | 7000
5 | Ceiling fan installation | Nos | 8 | 650 | 10 | 650 | 5200 | 6500
6 | MCB installation - 32A | Nos | 6 | 450 | 5 | 450 | 2700 | 2250
7 | Panel board installation | Nos | 1 | 15000 | 1 | 15000 | 15000 | 15000
8 | Conduit pipe installation | Meter | 300 | 35 | 350 | 35 | 10500 | 12250
9 | Cable laying - 4 sq mm | Meter | 200 | 65 | 180 | 65 | 13000 | 11700
10 | Light fixtures installation | Nos | 25 | 350 | 28 | 350 | 8750 | 9800