## Sheet1
BILL OF QUANTITIES
Name of Contractor or supplier : | M/s Seema Electrical Udaipur
Name of Work ;- | Electric Repair and MTC work at Govt. Ambedkar hostel Ambamata, Govardhanvilas, Udaipur
Serial No. of this bill : | First & Final Bill
No. and date of the last bill- | Not Applicable
Reference to work order or Agreement : | 1179 Dt. 09-01-2025
Agreement No. | 48/2024-25
Date of written order to commence work : | 09-01-2025
St. date of Start : | 18-01-2025
St. date of completion : | 17-04-2025
Date of actual completion of work : | 01-03-2025
Date of measurement : | 03-03-2025
WORK ORDER AMOUNT RS. | 854678
ITEM DETAILS
S_No | Item_Description | Unit | Work_Order_Qty | Work_Order_Rate | Bill_Qty | Bill_Rate | Work_Order_Amount | Bill_Amount
1 | Item 1 - Electrical work 1 | Piece | 58 | 826 | 58 | 826 | 47908 | 47908
2 | Item 2 - Electrical work 2 | Set | 21 | 1445 | 21 | 1445 | 30345 | 30345
3 | Item 3 - Electrical work 3 | Meter | 19 | 3680 | 19 | 3680 | 69920 | 69920
4 | Item 4 - Electrical work 4 | Meter | 23 | 2903 | 23 | 2903 | 66769 | 66769
5 | Item 5 - Electrical work 5 | Set | 47 | 1718 | 47 | 1718 | 80746 | 80746
6 | Item 6 - Electrical work 6 | Piece | 28 | 790 | 37 | 790 | 22120 | 29230
7 | Item 7 - Electrical work 7 | Nos | 26 | 1115 | 26 | 1115 | 28990 | 28990
8 | Item 8 - Electrical work 8 | Piece | 9 | 3365 | 9 | 3365 | 30285 | 30285
9 | Item 9 - Electrical work 9 | Nos | 32 | 3653 | 27 | 3653 | 116896 | 98631
10 | Item 10 - Electrical work 10 | Meter | 76 | 1762 | 76 | 1762 | 133912 | 133912
11 | Item 11 - Electrical work 11 | Set | 23 | 586 | 23 | 586 | 13478 | 13478
12 | Item 12 - Electrical work 12 | Set | 69 | 2334 | 78 | 2334 | 161046 | 182052
13 | Item 13 - Electrical work 13 | Nos | 4 | 3171 | 4 | 3171 | 12684 | 12684
14 | Item 14 - Electrical work 14 | Meter | 68 | 1625 | 68 | 1625 | 110500 | 110500
15 | Item 15 - Electrical work 15 | Nos | 54 | 2065 | 58 | 2065 | 111510 | 119770
16 | Item 16 - Electrical work 16 | Nos | 93 | 3389 | 93 | 3389 | 315177 | 315177
17 | Item 17 - Electrical work 17 | Nos | 93 | 1396 | 93 | 1396 | 129828 | 129828
18 | Item 18 - Electrical work 18 | Piece | 91 | 4748 | 99 | 4748 | 432068 | 470052
19 | Item 19 - Electrical work 19 | Set | 75 | 1298 | 75 | 1298 | 97350 | 97350
20 | Item 20 - Electrical work 20 | Nos | 96 | 701 | 96 | 701 | 67296 | 67296